## Sheet1
PSI010.2021 | 2021-02-18 | VRM | NRLS or StEIS | Trigger: New MH innovation & StEIS incident 2021/1743 | Oxehealth/Oxevision for inpatient suicide prevention | Unlikely | SJ | done | Email update 24/08/2023: in consideration of closure in relation to action 1 from June 2022, SJ has asked HP if there were any tangible outcomes from the WG and if therefore a PS Alert was appropriate. HP notes following her last correspondence with SJ I have no new update. I have not been included in any further working groups or updates on progress. Nothing useful or relevant came from the one WG I attended. FWo and GK discussed and support closure (email on file). Issue now closed. | No | Complete | Yes | 2023-08-24 | Yes | Archive - PS Issues as of 01.09.2021 - (upto PSI068.2021)
Email update from SJ on 21/08/2023:SJ notes this email (saved on file) relates to our response to join a meeting to discuss a public campaign to stop the use of Oxehealth/Oxevision. We have declined this meeting as noted within the email stating The ongoing issues in relation to Oxevision / Oxehealth do not appear to relate to any specific patient safety concerns but to broader safeguarding and surveillance issues. It therefore does not feel necessary to include a patient safety rep on the group at this time. If, however, during discussions any specific patient safety concerns come to light then please feel free to loop the patient safety team back in.
Update provided at VRM on 9/6/2022: SJ provided an overview of all the work that has been achieved to date. DHTs are growing exponentially and therefore although this may have been considered new or under-recognised this intervention has led to both increased regulatory awareness through the MHRA and also within the mental health arena. The Working Group to review vision based patient monitoring technologies will hopefully establish standards for such products to ensure there is full review of training and education materials, the purpose of the technology and also the process for consent and patient awareness and understanding. All actions have been completed. Heather Pritchard is in touch with Heather Caudol and Oxehealth has set up a MH working group. MHSIP will keep a close eye on developments. Oxehealth will serve as an example for future technologies coming onto the market that could have clinical implications. Agreed there was still potential for an alert, particularly if it is about adhering to a framework when introducing new technologies.
Actions:
1. VRM agreed all actions have been completed and this issue has now been taken on by the right groups, therefore can now be closed to VRM, but keep open on the TL to check in 3-4mths as to whether there are any tangible outcomes from the working group HP sits on and consider if an alert would be appropriate, if not close completely.
2. Flag as a potential future R&R case study - would need to be discreet on wording due to subject matter.
Email update from SJ on 6/6/2022: done and update coming to VRM 9th June
FWo confirmed on 24/5/2022 SJ to take over this issue from FH
KK 23/3/2022: Flag for TL Review meeting to allocate issue to new lead following FH retirement.
Update provided at VRM on 17/3/2022: Email summary on file. Key actions have been in MHRA's gift and they are steadily making progress on making changes to how oxehealth should be used to prevent suicide and falls etc. MHRA is going to share the miniscope with Oxehealth as they would like to learn from our findings - this may instigate a regular feed of data via a DSA. HC is keeping on top of the quality of materials produced by Oxehealth. Although not currently at the point for future action, it was suggested that leaflets and training materials/guides could be produced - taking into consideration that those trusts who already use the device may not pick up on new materials/resources. The question of potential need for research was posed in the miniscope but not a formal VRM action but Taofikat may consider as a potential policy research application stream for MTM to consider for next publication.
Email update from FH on 18/10/2021: MHRA have worked on some of our concerns and we (FH and GK or SJ) are meeting with MHRA and Oxehealth on 27 October.
Email update from SJ 08/06/2021:
SJ actions recorded below, completed; evd shared with MHRA and their response saved in file.
Update provided at VRM on 27/6/2021: FH presented the findings of her comprehensive background search and NRLS review. Some findings raised concern and had VRM revert to the flowchart to consider if this fell within the alerting zone.
Actions:
1. SJ to raise with MHRA mismatch between medical claims on website and IfU using only the vital signs tracker is a medical device; especially active risk to patient safety if website materials imply to patients or staff it has automatic alerting functionalities it does not have
2. SJ to raise with MHRA difficulty accessing IfU, which even at the technical level of how to use the vital signs risk reliance of users on website which does not include cautions and contraindications
3. SJ to raise with MHRA no information on safe fitting of monitors to avoid ligature risk when monitors linked to the medical device; incident of unsafe fitting reported and providers would be unable to check if no information on safe installation made available outside company. If this is not fruitful, may have to take through Estates and Facilities route
4. HC to take forward discussion with MHSIP how to best take forward; likely initial meeting with MHSIP plus one or more MH Chief Nurses supporting the MHSIP programme to discuss how to make users and future users of Oxehealth more aware of challenges of avoiding unintended consequences, and risks of staff and patient belief mismatch with device functionality leading to false reassurance that help will be automatically summoned. Best routes and timings need to be considered, but VRM supports findings of miniscope being fully understood by senior leaders in all organisations using or introducing the device.
5. Potential for alert to be revisited if any other workstreams identify clear constructive actions
First discussed at VRM on 18/2/2021: FH presented this issue which has arisen following an issue Aiden has been involved with involving new technology claiming to help prevent suicide attempts and falls in older inpatients; and a look at data identified an incident whereby there was a possible delay in reaching a MH pt, as staff alerted to a missing patient and went to central video screen as opposed to directly locating patient in private area, the alarms do not appear to have alerted staff to patient not breathing. It was suggested that the new technology may cause new risks such as false beliefs and reassurance. SJ noted that new technology under new brexit rules need to be registered with MHRA by September and this should provide some oversight. The website describing the tech does not provide sufficient evidence that the functions work efficiently, e.g. how do the sensors in the ceiling work to monitor pulse and respiratory rates from afar? SJ agreed to look into this from a curiosity perspective (not an action). It was also noted whether patients are aware they are being survyed and if they are does this add another element of risk that the patients feel safer and feel more likely to be rescued following attempts of self harm/suicide, so more likely to self harm?
Action:
1. FH (with support on NRLS search and data extraction) to carry out review of NRLS search. Tight search to incorporate specific terms Oxehealth, Oxevision and spelling variations.